Production of Macao Promotional Videos and TV Commercials in 2020

Tentative Production Schedule

Week 1-2		De-briefing meeting

Revised storyboards & scripts

Week 3-4		Pre-production

Approval of storyboards & scripts

Casting and Location scout

Week 5		Pre-production meeting with client

Talent and Wardrobes styling

Week 6		Final Pre-production

Wardrobes fitting and Technical scout

Week 7-8		Location Shooting in Macao for 10 to 15 days

Week 8		Offline editing

Week 9		Presentation of 1st rough cut

Offline revision

Week 9		Final revision and approval of offline by client

Week 10		Online editing

Week 10		Presentation of 1st online

Week 11		Final revision and approval of online by client

Week 12		Delivery of client copies